NORTH DAYI DISTRICT ASSEMBLY

ANNUAL ACTION PLAN, 2022

Prepared By:

District Planning Coordinating Unit (DPCU)

North Dayi District Assembly

Anfoega

OCTOBER, 2021

Table of Contents

1.1	PHYSICAL CHARACTERISTICS	2

1.1.1	LOCATION	2

1.1.2	CLIMATE OF THE DISTRICT.	3

1.1.3	VEGETATION OF THE DISTRICT.	3

1.1.4	DRAINAGE	4

1.1.5	TOPOGRAPHY	4

1.1.6	GEOLOGY AND MINERALS	5

1.1.7 BIODIVERSITY, CLIMATE CHANGE AND GREEN ECONOMY	5

1.1.8 NATURAL AND MAN-MADE DISASTERS	6

1.1.9 NATURAL RESOURCE UTILIZATION	6

1.1.10 CHALLENGES FOR THE USE OF NATURAL RESOURCE	7

1.2	GENERAL INTRODUCTION	7

TABLE 1.1 MATRIX showing Annual Action Plan, 2022	9

DISTRICT PROFILE

## PHYSICAL CHARACTERISTICS

## LOCATION

The North Dayi District is located in the Volta Region of Ghana and it was established by the Legislative Instrument LI 2076 of 2012. The office of the North Dayi District Assembly is located in Anfoega.  The District is about 70km away from Ho where the Office of the Volta Regional Minister is located and 250Km away from Accra, the seat of Government.

The District lies within latitudes 60 20’N and 70 05’N, and Longitude 00 17’E. It shares boundaries with Kpando Municipal to the North, South Dayi District to the south, and Afadzato South District to the East and the Volta Lake to the west. The Lake stretches over 80km of the coastal line, demarcates the Western boundary.

The District covers a total land area of 462.8 square kilometers representing 2.2% of the Volta Region with almost 30% of the land being covered by the Volta Lake. The District is rural and has over sixty (60) settlements. The District is basically agrarian with the sector providing jobs to a large section of the population and contributing significantly to the Local Economy. Economically active communities in the District are Anfoega and Vakpo.

## CLIMATE OF THE DISTRICT.

The District falls within the tropical equatorial zone, it is generally influenced by the South West Monsoons winds from the South Atlantic Ocean and the dry Harmattan winds from the Sahara. The District is characterized by double-maxima rainfall pattern with average annual rainfall ranging from 900mm to 1,300mm. The rainfall pattern support the cultivation of variety of crops including cash crops throughout the year. Eg. Cocoa, coffee etc.

The major raining season occurs from mid-April to early July and the minor from September to November.  The District normally experience variations in the seasons which affect agricultural activities in the District.

The mean annual temperature is about 270 Celsius, whereas the daily mean ranges from, 220 to 330 Celsius. The months of February and March are characterized usually with hot temperatures while July and August are of relatively cold.

## VEGETATION OF THE DISTRICT.

The vegetation of the District is a mix of guinea savannah woodland and semi-deciduous forest.   The savannah woodlands consist of grass with scattered trees like acacia, bamboo and baobabs. These dots the River Dayi Basin.  The semi-deciduous forests are found on the slopes of the Akwapim –Togo –Attakora ranges with many tree species which are also found in high forest zone, such as Antiaris toxicaria chechen, milicia excels (Odum) and Oil palm.

The situation described above is to a large extend has been destroyed. There is a gross misconduct on the part of citizens as regards the vegetation. Primarily Human Activities that destroy the vegetation as pertain in the District are: inappropriate farming practices, use of unauthorized chemicals, misapplication of chemicals, excessive logging and lumbering, charcoal burning, Development of settlement, construction of major infrastructure etc.

The activities above cause damages to the vegetation. Some of the issues are: Lost of forest cover, Biodiversity loss, Loss of organic materials, loss of soil fertility, erosion, Climate change and variability, loss of water resources, air pollution etc. All these damages have detrimental effects on human existence.

In an attempt to conserve the environment and protect the vegetative cover, the Forestry Commission under the FORUM project developed some forest reserves in the District. These are the Awate and Tsrukpe forest reserves, Wusuta, Aveme Sabadu, Vakpo, Botoku and Tsoxor forest reserves. Citizens have started destroying the forest reserves.

## DRAINAGE

The Volta Lake and the River Dayi are the major water bodies that drain the district. There are other numerous streams and rivulets that are found throughout the district. These rivers and streams are more or less perennial.

The Volta Lake is the largest water resource in the district. It runs along the whole of the western corridor with big potential for irrigation, aqua-culture and fishing. The District relies on the Lake for fish both for local consumption and export to towns within the country.  The River Dayi is the second largest water resource in the District, and its basin provides a prime farming land for the cultivation of a variety of food crop and vegetables. The presence of these water bodies is a great potential for supporting economic activities which can generate employment opportunities for the youth.

The Volta Lake and river Dayi are critical resources in the District that can Support commercial agriculture, small and medium size Irrigation schemes, vegetable cultivation, water transport, Commercial fish farming, Potable water schemes, tourism and eco-tourism etc.

## TOPOGRAPHY

The obvious physical features of the District are the Akwapim-Togo-Atakora ranges which is at the eastern corridor between Ho and Kpando Districts. The District is dotted with scattered hills and ranges of varied length and height resulting in an undulating feature of the District. The major hills are around Anfoega, Awate, Botoku and Wusuta. The highest point in the District is about 1,250 ft. and is located along the Volta Lake around Awate and Botoku. The hilly nature of the District predispose the District to poverty and also a potential for development. The presence of the hills is the reason for massive erosion in the District affecting settlement development, The Mountains have also covered several acres of land making arable land very scares hence low productivity.

It is common for people to think that mountain contains mineral resources, even though no prospective study have been conducted but residence hold the view that they (mountains) contains some essential minerals.  The mountains are currently the mining point of kaolin on small scale. Kaolin is a critical raw material in the construction industry, it is used for paint and other materials. Commercial mining will promote economic growth and development. The mountains also contains rocks that can aid the construction industry and tourism development.

On agriculture, farm lands are relatively uncommon due to the presence of the mountains by implication the department of Agriculture should adopt best farming practices to increase productivity. Eg. The use of good farming techniques, improve seeds, use of local manures to sustain the nutrients in the soil.

## GEOLOGY AND MINERALS

The District is generally underlain by Buem Volcanic rocks stretching through to Jasikan and Kadjebi Districts. The implication of this type of rock is that it supports surface supplies of underground water and the surface supplies are fairly good while prospects for boreholes ranges from fair to good. The major soil types developed from this parent rock in the District are the Savannah Ochrosols (reddish, lightly acid; more nutrient) “Oxysol” (heavily drained; yellowish; less nutrient and ground water laterites. This is characterized by sandy loam type of soil with local adaptation. Along the lake and the River Dayi, the alluvial silt loams predominate. The terrain is mostly steep and sometimes gentle resulting in difficulty to access. Inventories made to classify soils according to their general and chemical characteristics indicate that the soils in the District are of low fertility and low moisture holding capacity which has serious implication for agricultural sub-sector. Irrigation schemes will support agricultural development in the District.

The District is relatively endowed with limited mineral deposits of economic importance. There are large deposits of Kaolin at Anfoega Agatanyigbe, Anfoega Bume and Botoku with different colour suitable for molding of bricks, tiles, paint etc. for the construction industry. North Dayi District Assembly can establish cottage industry in pottery and ceramics taking advantage of the mineral deposit by extension create jobs.

### 1.1.7 BIODIVERSITY, CLIMATE CHANGE AND GREEN ECONOMY

The effects of climate change and its vulnerability can be felt across the length and breadth of the District due to its agrarian nature.  North Dayi District is home to four (4) forest reserves (Dayi Block forest reserve, West Block forest reserve and others) endowed with several economic trees, fruit and other tree species which serves as home to hundreds of thousands of animals species. Not to talk about these forests serving as shade to the numerous springs, streams and rivers that run the length and breadth of the District.

North Dayi District has witnessed persistent depletion of the forest, bio-diversity, water resources and other aquatic species.

The District is experiencing a destruction of its ecosystem and natural resource base through the following factors;

- Destruction of forests through encroachment into forest reserves and exploitation of economic timber species without permit

- Annual bush fires

- Inappropriate farming practices and deforestation, destruction of vegetation and the ecological systems through cultivation on slopes and on the lands adjoining rivers and streams

- Encroachment into and destruction of wildlife sanctuary through uncontrolled hunting and other human activities

- Winning of sand, quarrying of stones and gravel for building and road construction

- Lack of enough education on the negative effects climate change

- Accelerated erosion resulting from removal of vegetative cover around dwellings and open spaces in settlements and absence of properly constructed drainage channels

- Non-management of domestic waste i.e.  rubbish and human excreta are disposed-off indiscriminately

- Little monitoring of the environmental impact of human activities and development projects

The Assembly with support from development partners will implement interventions programmes to mitigate the impacts of this trends in the District.

# 1.1.8 NATURAL AND MAN-MADE DISASTERS

A disaster is a  distraction occurring over a relatively short time of the functioning of a community or a society involving wide spread human, material, economic or environmental loss and impacts which normally  exceeds the ability of the affected community or society to cope using its own resources.

The North Dayi District is prone to both natural and man-made disasters, ranging from water Transport disasters, motor incidents (okada) Meteorological disasters, Disease and Epidemic Outbreaks, Domestic and Bush Fires, Pest and Infestation of Farms and Crops, black flies,  Natural Resource destruction activities like deforestation, pollution of water bodies etc.

# 1.1.9 NATURAL RESOURCE UTILIZATION

The natural resources available to the district can generally be grouped under forest reserves, arable land, water resources (Lake Volta, River Dayi) and mineral resources.  The forest reserve is a local one which is utilized for research purposes, recreation and also serves as a tourist site.

The arable land (fertile lands) are basically used for farming activities and sustainable farming can be used for the extraction of the resource.

The water resources are mainly the rivers in the district and the lake volta. They are used for irrigation, fishing and as a tourist site. Again sustainable fishing activities are the technologies that can be used for their extraction.

The mineral resource is mainly white clay which is basically chewed by women in the district. The available technology for its extraction is the use of hoes. Mechanized sustainable extraction can be another technology for its extraction and in order to enhance its utilization, it can be used for paints, ceramics and tiles.

## 1.1.10 CHALLENGES FOR THE USE OF NATURAL RESOURCE

The listed challenges as faced by the district with respect to their natural resources include; the unapproved usage of agro-chemicals for farming, the activities of illegal chain saw operators in the reserves, the use of unapproved fishing methods and the difficulty in finding other uses for the white clay.

## GENERAL INTRODUCTION

The North Dayi District Assembly per the National Development Planning System Act 1994, (Act 480) National Development Planning (System) Regulation 2016, LI 2232, the Local Governance Act, 2016 Act 936 is mandated to prepare plans to guide the development of the District. The District is again mandated to prepare reports on progress based on monitoring of development projects and programmes conducted. The District every four years commits significant amount of resources, both human and financial to prepare Medium Term Development Plan from which Annual Action Plans are extracted every year up to four years.

This activity is preceded by a thorough needs assessment and other stakeholder engagements to update needs of the people per the needs assessment conducted during the preparation of the DMTDP.

The Development Dimensions of the District Medium Term Development Plan 2022-2025 are the following:

- Economic Development

- Social Development

- Environment, Infrastructure and Human settlement

- Governance, Corruption and Public Accountability

Table 1.1 below is the Annual Action Plan for 2022, this constitute programmes and projects for implementation and ongoing programmes and projects are rolled on from the 2021 Annual Action Plan.

TABLE 1.1 MATRIX showing Annual Action Plan, 2022

| Programme (PBB) | Sub-programme | Programme/Project | Location | Timeframe (Qtrs) |  |  |  | Cost |  |  |  |  | Prog. Status |  | Implementing Institution |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | GOG | DACF | DACF-RFG | IGF | Others | New | On-going | Lead | Coll. |
| Goal: To improve fiscal performance of the Assembly Objective: To improve IGF performance by 20% annually within the planned |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Finance and revenue mobilization | Conduct Routine monitoring of revenue collectors. | District wide | X | X | X | X |  |  |  | 2,500.00 |  | xxx |  | Fin. Dep’t | Budget Unit |
|  |  | Organise quarterly sensitization programmes on revenue mobilization and utilization (Radio programmes, town hall meetings etc.) | Anfoega and other communities. | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | Fin. Dep’t | Cent Adm/Budget Unit |
|  |  | Organize 2No. training workshops on effective revenue mobilization for 15 revenue collectors | Anfoega | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | Fin. Dep’t | Budget Unit/HR Dept |
|  |  | Procure and sell 1,500 vehicle and motor stickers | Anfoega | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | Fin. Dep’t | Proc /Budget Unit. |
|  |  | Form and inaugurate revenue mobilization taskforce | Anfoega | X | X | X | X |  |  |  | 1,000.00 |  | xxx |  | Fin. Dep’t | Budget Unit |
|  |  | Update revenue data base to include new structures. | Anfoega | X | X | X | X |  |  |  | 100,000.00 |  | xxx |  | Proc. Unit | Fin. Dep’t/Budget Unit |
|  |  | Collaborate with GIZ for dL Rev software and other supports annually. | Anfoega | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | Finance Dep’t | GIZ |
|  |  | Print and distribute 1500 demand notices annually (3200) | Anfoega | X | X | X | X |  |  |  | 8000.00 |  | xxx |  | Finance Dep’t | Cent Adm/Budget Unit |
|  |  | Print and distribute 1500 property rate bills for distribution and collection. | Anfoega | X | X | X | X |  |  |  | 10,000.00 |  | xxx |  | Fin. Dep’t | Cent Adm/Budget Unit |
| Goal: To promote accountability and transparency in the system of local governance at all levels To promote effective participation of PWD’s in governance at all levels Objective: To improve effective popular participation in planning, budgeting other governance activities of the Assembly by at all levels annually by the end of the planned period including PWDs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General Administration | Organize 4No. town hall meetings with Six (6) sub-district structures |  | X | X | X | X |  | 20,000.00 |  |  |  | xxx |  | Plg Unit | CentAdm/Budget Unit |
|  |  | Convene 4No. General Assembly meetings | Anfoega |  |  |  |  |  |  |  | 30,000.00 |  | xxx |  | Cent Admin | Office of the PM |
|  |  | Convene 4No. Executive Committee (EXECO) meetings | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Cent Admin |  |
|  |  | Organize 4No. five statutory sub-committees meetings | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Cent Admin |  |
|  |  | Organize 1No. Independence Day Anniversary celebrations | Selected community | X | X | X | X |  | 15,000.00 |  |  |  | xxx |  | Cent Admin | DE Dir. |
|  |  | Organize 1No. Republic Day celebrations | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Cent Admin | Pensioners |
|  |  | Organize 4No. Audit Committee meetings | Anfoega | X | X | X | X |  | 12,000.00 |  |  |  | xxx |  | Int. Audit Unit | Cent Adm |
|  |  | Organize 4No. budget Committee meetings | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Budget Unit | Cent Adm |
|  |  | Organize 4No. DPCU meetings | Anfoega | X | X | X | X |  | 15,000.00 |  |  |  | xxx |  | Plg Unit | Cent Adm |
|  |  | Organize 4No. Entity Tender Committee meetings | Anfoega | X | X | X | X |  |  |  | 10,000.00 |  |  |  | Proc. Unit |  |
|  |  | Organize 4No. Management meetings | Anfoega | X | X | X | X |  |  |  | 10,000.00 |  |  |  | Cent Admin Dept | HR Dep’t |
|  |  | Organize 4No. staff meetings | Anfoega | X | X | X | X |  |  |  | 8,000.00 |  |  |  | Cent Admin Dept | HR Dep’t |
|  |  | Organize 4No. PRCC meetings | Anfoega | X | X | X | X |  | 16,000.00 |  |  |  |  |  | Cent Adm |  |
|  |  | Organize quarterly radio programme on Government policies and Assembly activities | District wide | X | X | X | X |  |  |  | 12,000.00 |  | xxx |  | Cent Admin Dept | NCCE/Inf |
|  |  | Pay ex-gratia of 34 Assembly members | Anfoega | X | X | X | X |  |  |  | 64,500.00 |  |  | xxx | Cent Admin | Fin Dept |
|  |  | Develop and gazette Assembly bye-law | Anfoega | X | X | X | X |  | 15,000.00 |  |  |  | xxx |  | Cent Admin |  |
| Goal: To deepen decentralization and popular participation in local governance Objective: To operationalize one sub-district structures annually by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General Administration | Construct and furnish office accommodation for Anfoega Area Council | Anfoega Vakpo | X | X | X | X |  | 400,000.00 |  |  |  | xxx |  | Cent Admin | DPCU |
|  |  | Procure office equipment for two Area councils (Anfoega and Vakpo Area Councils) | Anfoega Vakpo | X | X | X | X |  | 20,000.00 |  |  |  | xxx |  | Cent Admin | Proc Unit/Fin Dept |
|  |  | Organize 1No. Capacity building for staff of Area Councils on planning, budgeting and resource mobilization | Anfoega | X | X | X | X |  | 12,000.00 |  |  |  | xxx |  | Cent Admin | HR/Plg Unit/Budget Unit |
|  |  | Provide financial support to communities for self-help initiated projects | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Cent. Adm. |  |
|  |  | Provide financial support to Six Area Councils to support sanitation and hygiene activities (clean-up exercises) | Anfoega | X | X | X | X |  | 8,000.00 |  |  |  | xxx |  | Cent. Adm. |  |
| Goal: Maintain a stable, united and safe society Objective: Deepen political, financial and administrative decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General Administration | Renovate 1No. District Assembly office complex. | Anfoega | X | X | X | X |  | 50,000.00 |  |  | 30,000.00 | xxx |  | Cent Adm. | DPCU/wks |
|  |  | Complete 10Unit office accommodation within the old Assembly Hall. | Anfoega | X | X | X | X |  | 120,000.00 |  |  |  |  | xxx | Cent Admi | DPCU/wks |
| Goal: To ensure the maximum utilization of available resource Objective: To reduce duplication of financial resources between the Assembly and DPs To assess the impact of interventions on the populace annually by the end of the planned period To improve resource efficiency and utilization annually by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | Planning, budgeting, monitoring and evaluation | Conduct quarterly monitoring of physical programmes and projects | District wide | X | X | X | X |  | 25,000.00 |  |  |  | xxx |  | Plg Unit | DPCU |
|  |  | Conduct quarterly monitoring of activities of six (6) sub- structures | District wide | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Plg Unit | DPCU |
|  |  | Embark on daily monitoring of teaching and learning across the District. | District wide | X | X | X | X | 50,000.00 |  |  |  |  | xxx |  | Educ Dep’t |  |
|  |  | Embark on quarterly monitoring of health facilities | District wide | X | X | X | X | 50,000.00 |  |  |  |  | xxx |  | Health Dep’t |  |
|  |  | Organise quarterly monitoring of operations of WSMTs in the District | District wide | X | X | X | X |  | 4,000.00 |  | 3,000.00 |  | xxx |  | DWST | Plg Unit/ EHSU |
|  |  | Organise monthly monitoring of beneficiary communities under Community Led Total Sanitation (CLTS) | District wide | X | X | X | X |  | 50,000.00 |  |  | 100,000.00 | xxx |  | EHSU | DICCS |
|  |  | Organise 1No. stakeholder consultation meeting on the review of 2022 fee-fixing Resolution (FFR) | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  |  |  | Budget Unit | Fin. Dep’t/ Cent Admin |
|  |  | Prepare District Medium Term Development Plan (2022 -2025) | Anfoega | X | X | X | X |  | 70,000.00 |  |  |  | xxx |  | Plg Unit | DPCU |
|  |  | Prepare and submit 2023 Annual Action Plan (AAP - 2023) | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Plg/Budget Units | Cent Adm |
|  |  | Prepare and submit 2022-2025 composite budget | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Plg/Budget Units | Cent Adm |
| Goal: To enhance the productivity of staff of the Assembly To promote databased decision making at all levels of the Assembly system Objective: To improve efficiency and effectiveness of staff by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | Human Resource Management | Service 11No. vehicles | Anfoega | X | X | X | X |  | 30,000.00 |  |  |  | xxx |  | Cent Admin | Transport Unit |
|  |  | Procure 4No. Lab tops and 2No. Desktop Computers. | Anfoega | X | X | X | X |  | 10,000.00 | 15,000.00 |  |  | xxx |  | Cent Admin |  |
|  |  | Service 14No. air-conditioners | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | Cent Admin |  |
|  |  | Service of 18No. Office laptop computers | Anfoega | X | X | X | X |  | 5,000.00 |  | 5,000.00 |  | xxx |  | Cent Admin |  |
|  |  | Training on Proposal Writing and contract management and administration. | Anfoega | X | X | X | X |  |  | 10,000.00 |  |  | xxx |  | HR Dep’t | Cent Admin |
|  |  | Organize 2No. Staff durbar for staff of North Dayi District Assembly. | Anfoega | X | X | X | X |  |  | 10,000.00 |  |  | xxx |  | HR Dep’t | Cent Admin |
|  |  | In service training on Court proceedings and prosecution for environmental Health Officers | Anfoega | X | X | X | X |  |  | 10,000.00 |  |  | xxx |  | HR Dep’t | Cent Admin |
|  |  | Organize 1No. training workshop on records management for records and management Staff | Anfoega | X | X | X | X |  |  | 18,000.00 |  |  | xxx |  | HR Dep’t | Cent Admin. |
|  |  | Train DPCU members on presentation of data and preparation of Progress Reports. | Anfoega | X | X | X | X |  |  |  | 5000.00 |  | xxx |  | HR Dep’t | Cent Admin. |
| Goal: To provide decent and safe accommodation for staff Objective: To reduce staff accommodation deficit from 70% to 40% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure delivery and management | Infrastructure development | Complete 2No. 2Unit seni-detatch staff bungalow at Anfoega Dzana | Anfoega Dzana | X | X | X | X |  | 50,000.00 |  |  |  |  | xxx | Cent Admin | DPCU/Wks Dept |
|  |  | Complete 2No. 2Unit seni-detatch staff bungalow at Anfoega Dzana | Anfoega Dzana | X | X | X | X |  | 50,000.00 |  |  |  |  | xxx | CODA | Cent Adm/Wks Dept |
|  |  | Construct 2No. 2Unit semi-detached Nurses bungalow | Vakpo | X | X | X | X |  |  | 450,000.00 |  |  | xxx |  | Central Admi | DPCU/wks Dept |
|  |  | Construct 2No. 2Unit semi-detached teachers bungalow | Anfoega | X | X | X | X |  |  | 450,000.00 |  |  | xxx |  | Central Admi | DPCU/wks Dept |
|  |  | Renovate 10No. staff bungalow. | District wide | X | X | X | X |  | 250,000.00 |  |  |  | xxx |  | Central Admi | DPCU/wks Dept |
| Goal: To ensure maximum security for all Objective: To reduce the incidence of crime by 50% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Legislative oversight | Complete the construction of 1No. District Police Headquarters at Anfoega. | Anfoega | X | X | X | X |  | 120,000.00 |  |  |  |  | xxx | Cent Admin | Works Dep’t/Plg Unit |
|  |  | Organize 12No. DISEC meetings | Anfoega | X | X | X | X |  | 24,000.00 |  |  |  | xxx |  | Cent Admin | Security Agencies |
|  |  | Construct police post at Aveme/Tsyome/ Sabadu Area Council | Aveme Danyigba | X | X | X | X |  |  | 500,000.00 |  |  | xxx |  | Cent Admin | Wks Dept |
|  |  | Support to District Security Agencies to maintain peace and security | Anfoega | X | X | X | X |  |  |  | 25,000.00 |  | xxx |  | Cent Admin | Security agencies |
| Goal: To promote integrated spatial development Objective: To increase the number of permits issued by 10% annually by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure delivery and management | Spatial planning | Organize 12No. Technical Planning Committee meetings | Anfoega | X | X | X | X |  |  |  | 120,000.00 |  | xxx |  | PPD | SPC/TSC |
|  |  | Organize 12No. Spatial Planning Committee meetings | Anfoega | X | X | X | X |  |  |  | 24,000.00 |  | xxx |  | PPD | SPC/TSC |
|  |  | Organize 4No. SAT meetings | Anfoega | X | X | X | X |  |  |  | 8,000.00 |  | xxx |  | PPD | SPC/TSC |
|  |  | Organize (12No.) public education programme on land use planning and building regulations | District wide | X | X | X | X |  | 12,000.00 |  |  |  |  |  | PPD | SPC/TSC |
|  |  | Land acquisition for North Dayi District Assembly | Anfoega | X | X | X | X |  | 50,000.00 |  |  |  | xxx |  | PPD | SPC/TSC/cent Adm |
|  |  | Prepare spatial development framework for the District | Anfoega | X | X | X | X |  | 40,000.00 |  |  |  | xxx |  | PPD | SPC/TSC |
|  |  | Digitize 9,500 properties out of 19,000 properties | District wide | X | X | X | X | 5,000.00 |  |  | 5,000.00 |  |  | xxx | PPD | SPC/TSC |
|  |  | Procure 200 street signage’s for street naming | District wide | X | X | X | X |  | 35,0000.00 |  |  |  |  | xxx | PPD | Wks Dept |
|  |  | Maintain 50No. street signage’s | District wide | X | X | X | X |  | 10,000.00 |  |  |  |  | xxx | PPD | Wks Dept |
|  |  | Stencil 9,500 properties out of 19,000 properties | District wide | X | X | X | X |  | 200,000.00 |  |  |  |  | xxx | PPD | Wks Dept |
|  |  | Prepare five (5) sector Local Planning schemes | Anfoega Vakpo Wusuta | X | X | X | X |  | 60,000.00 |  |  |  | xxx |  | PPD | Wks Dept |
| Goal: To expand and enhance access to quality telecommunication network services by all Objective: To improve telecommunication network coverage from 60% to 85% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure delivery and management | Infrastructure development | Facilitate extension of telecommunication network services to five (7) communities | 7 communities | X | X | X | X |  |  |  | 10,000.00 |  | xxx |  | Cent Admin | GIFEC |
|  |  | Provide internet service for the E-library at Botoku. | Botoku | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | Cent Adm | GIFEC |
| Goal: To improve the transportation system Objective: To improve the safety and security of all categories of road users by the end of the planned period To reduce post-harvest losses from 40% to 10% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure development | Complete the Rehabilitation of 170m feeder Raod at Anfoega Adame | Anfoega Adame | X | X | X | X |  | 100,000.00 |  |  |  |  | xxx | Cent Admin | Wks Dept/Dept |
|  |  | Complete the Rehabilitation of Wusuta – Botoku Feeder Road | Wusuta -Botoku | X | X | X | X |  |  |  |  | 350,000.00 |  | xxx | CoDA | Cent Admin |
|  |  | Open up link road from Anfoega Dzana- Anfoega Wadamaxe. | Anfoega Dzana-Wadamaxe | X | X | X | X |  |  | 500,000.00 |  |  | xxx |  | Cent Adm | DPCU/Wks |
|  |  | Complete construction of Tsrukpe –Zanu Kope Feeder Road (6.4km) |  | X | X | X | X | 224,000.00 |  |  |  |  |  | xxx | Cent Adm | GPSNP |
|  |  | Rehabilitation Vakpo Todzi Cemetery feeder (1.18km) | Vakpo Todzi | X | X | X | X |  | 15,000.00 |  |  |  |  | xxx | Cent Adm | Wks |
|  |  | Supervise the completion of Anforga Akokorme – Wadamaxe Road. | Wadamaxe | X | X | X | X |  |  |  | 20,000.00 |  |  |  | Cent Admin | Dep’t of F. R. |
|  |  | Complete construction of Vakpo - Wusuta Road. | Wusuta | X | X | X | X | 150,000,000.00 |  |  |  |  |  | xxx | Cent Adm | De’t of F. R. |
|  |  | Rehabilitation of Wusuta – Wusuta Kpebe Road. | Wusuta Kpebe | X | X | X | X | 3,000,000.00 |  |  |  |  |  | xxx | Cent Adm | Dep’t of F. R |
| Goal: To expand access to reliable national grid by all Objective: To improve access to electricity from 85% to 100% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure development | Facilitate the installation of solar lights in off-grid communities | Botoku Brada Tornu | X | X | X | X |  | 35,000.00 |  |  |  | xxx |  | Cent Admin | Wks Dept/ MoE |
|  |  | Extend electricity to newly developed areas across the District. | District wide | X | X | X | X |  | 45,000.00 |  |  |  | xxx |  | Cent Admin | Wks Dept/ MoE |
|  |  | Procure and install 150No. Street lights across the District | Selected communities | X | X | X | X |  |  | 60,000.00 |  |  | xxx |  | Cent Admin | Wks Dept/ECG |
|  |  | Maintain 100No. street light across the District | District wide | X | X | X | X |  |  | 350,000.00 |  |  | xxx |  | Cent Admin | Wks Dept/ECG |
| Goal: To protect and preserve the natural environment including forest in a sustainable manner To ensure resilience against the impact of climate change at all levels Objectives: To reduce the rate of bush fires by 0% annually by the end of the planned period To reduce soil degradation by 10% annually by the end of the planned period To mitigate the impact of climate change on households by 10% annually by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental Development | Disaster Prevention and Management | Organize public education and sensitization on bush/domestic fire and deforestation | Anfoega | X | X | X | X |  | 5,000.00 |  |  |  | xxx |  | NADMO | Fire Service |
|  |  | Community engagement with farmers, charcoal burners, chainsaw operators and other stakeholders. | Anfoega | X | X | X | X |  | 4,000.00 |  |  |  | xxx |  | NADMO |  |
|  |  | Planting of Thirty thousand (30,000) economic trees across the District | District wide | X | X | X | X |  | 10,000.00 |  | 5,000.00 |  | xxx |  | NADMO | Fire Service |
|  |  | Formation of ecological protection clubs in the various secondary schools. | Anfoega and Vakpo | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | NADMO | Cent Admin |
|  |  | Nurturing of tree planted under the Green Ghana Project. | Tutukpene | X | X | X | X |  | 5,000.00 |  | 2,000.00 |  |  | xxx | NADMO | Agric |
| Goal: To expand social protection programmes to cover all eligible household Objective: To increase LEAP beneficiary households by 10% by the end of the planned period To increase the percentage of registered indigents onto NHIS by 5% annually To improve the livelihoods of 70 PWDs annually by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services delivery | Social Welfare and Community Development | Supervise payment of LEAP grants to beneficiaries in 22 payment centres. | District wide | X | X | X | X |  | 5000.00 |  |  |  | xxx |  | SWCD | Cent. Admi./FFin.Dep. |
|  |  | Enrollment of LEAP beneficiaries and households on to NHIS and renewal of subscription. | District wide | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | SWCD | Cent. Admi. |
|  |  | Provide financial assistance to Persons with Disabilities (PWDs) in the District | District wide | X | X | X | X |  | 260,000.00 |  |  |  | xxx |  | SWCD |  |
|  |  | Provide financial support to organization of PWDs/ Association for workshop/seminars/meetings | District wide | X | X | X | X |  | 5000.00 |  |  |  | xx |  | SWCD | Cent Admi./Fin. Dept |
|  |  | Quarterly Monitoring of beneficiaries of PWDs funds and support. | District wide | X | X | X | X |  | 10,000.00 |  |  |  | xx |  | SWCD | Cent. Admi./Fin. Dept |
|  |  | To enroll PWDs on to NHIS and renewal of subscription for expired cards. | Anfoega | X | X | X | X |  | 15,000.00 |  |  |  | xx |  | SWCD | Cent. Admi./Fin. Dept |
|  |  | To sensitize organization of PWDs on Disability Fund | District wide | X | X | X | X |  | 15,000.00 |  |  |  | xx |  | SWCD | DPCU |
| Goal: To promote and protect the rights of every child from all forms of abuse To eliminate teenage pregnancy Objectives: To reduce child related abuse cases by 10% by the end of the planned period To reduce teenage pregnancy by 10% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services delivery | Social Welfare and Community Development | Conduct 1No. ISSOP training for child protection stakeholders | Anfoega | X | X | X | X |  |  |  |  | 5000.00 | xx |  | SWCD | UNICEF |
|  |  | Conduct home study prospective foster parents | District wide | X | X | X | X |  | 5,000.00 |  |  |  | xx |  | SWCD | Cent Adm |
|  |  | Organise 1No. orientation on foster care | Anfoega | X | X | X | X |  | 5000.00 |  |  |  | xx |  | SWCD | CentAdm |
|  |  | UN international Child Labour day celebration | Vakpo | X | X | X | X |  | 10,000.00 |  |  |  | xx |  | SWCD | CentAdm |
|  |  | Ensure effective handling Child Custody, Maintenance cases and make follow up to communities (case management) | Anfoega | X | X | X | X |  | 5,000.00 |  |  |  | xx |  | SWCD | CentAdm |
|  |  | Support for integrated social services delivery and case management follow ups meetings and orientation training) | District wide | X | X | X | X |  |  |  |  | 15,000.00 | xxx |  | SWCD | UNICEF |
|  |  | To engage (20) communities on Child Rights promotion and protection using (CP tool kit) | District wide | X | X | X | X |  |  |  |  | 15,000.00 | xxx |  | SWCD | UNICEF |
|  |  | To organize 2No. Sensitization/ education on Domestic violence/ Gender base violence. | Anfoega | X | X | X | X |  | 8000.00 |  |  |  | xxx |  | SWCD | CentAdm |
|  |  | Sensitize 10 communities on child labour and trafficking. | Selected communities | X | X | X | X |  | 8000.00 |  |  |  | xxx |  | SWCD | CentAdm |
|  |  | To form women groups in 5 communities and follow on their activities. | District wide | X | X | X | X |  | 7000.00 |  |  |  | xxx |  | SWCD | CentAdm |
|  |  | To empower women group in 3 communities with economic skills training such as soap making, beads etc. | Selected communities | X | X | X | X |  | 7000.00 |  |  |  | xxx |  | SWCD | CentAdm |
|  |  | Visit and monitor Day Care Centres in the District. | District wide | X | X | X | X |  | 5,000.00 |  |  |  |  |  | SWCD | Cent Adm |
| Goal: To improve environmental sanitation To improve access to sustainable safe water for all Objective: To improve ODF coverage by 57% by the end of the planned period To improve safe water coverage from 70% to 90% by the end of the planned period Mainstream emergency planning and preparedness into Ghana’s development planning agenda at all levels to respond to potential internal and external threats (including COVID-19) Objective: Enhance industry resilience to shocks (e.g., COVID-19) Mitigate the impact of COVID-19 on the implementation of projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services delivery | Environmental Health delivery | Field facilitators weekly monitoring in thirty (30). Communities | 30 communities | X | X | X | X |  |  |  | 33, 600.00 |  | xxx |  | EHSU | UNICEF |
|  |  | Monthly activities of natural leaders in 30 communities (intercom munity verifications, meetings, etc.) | 30 communities | X | X | X | X |  |  |  | 5,500.00 |  | xxx |  | EHSU | UNICEF |
|  |  | Convene 12No. DICCS meetings | Anfoega | X | X | X | X |  |  |  | 4,500.00 |  | xxx |  | EHSU | UNICEF |
|  |  | Organize 12 No. field facilitators monthly review meetings | Anfoega | X | X | X | X |  |  |  |  | 5,500.00 | xxx |  | EHSU | Finance Dept |
|  |  | Quarterly radio discussion programs. | Anfoega | X | X | X | X |  | 1000.00 |  |  |  | xxx |  | EHSU | Cent. Admi. |
|  |  | DICCS monitoring of 30 communities | Selected communities | X | X | X | X |  |  |  |  | 4,500.00 | xxx |  | EHSU | UNICEF |
|  |  | ODF celebration (Awards to 9 ODF communities) | 20 communities | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | EHSU | Cent. Admi. |
|  |  | School health education activities in 30 selected schools in the District | Selected Schools | X | X | X | X |  | 5,000.00 |  |  |  | xxx |  | EHSU | Cent. Admi./GES |
|  |  | Facilitate the provision 30 hand washing facilities in 30 school | Selected schools | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | EHSU | Cent. Admi./UNICEF |
|  |  | Medical screening and health education to 2000 food and drink handlers | District wide | X | X | X | X |  | 5,000.00 |  |  |  | xxx |  | EHSU | Cent. Admi./ consult. |
|  |  | Construction of 1No. Slaughter House and 1No. meat shop at Vakpo | Vakpo | X | X | X | X |  |  | 145,000.00 |  |  | xxx |  | EHSU | Cent. Admi. |
|  |  | Arrest and impound at least 500 stray animals | District wide | X | X | X | X |  |  |  | 5000.00 |  | xxx |  | EHSU | Cent. Admi. |
|  |  | Dislodged public/School toilets(10 trips/yeas) | District wide | X | X | X | X |  | 15,000.00 |  |  |  | xxx |  | EHSU | Cent. Admi. |
|  |  | Sitting and acquisition of liquid waste disposal site | Anfoega | X | X | X | X |  | 25,000.00 |  |  |  | xxx |  | Cent Admin | Wks Dept/ EHSU |
|  |  | Facilitate the acquisition of at least 100 refuse containers by household | Anfoega | X | X | X | X |  | 3000.00 |  |  |  | xxx |  | Cent Admin | Zoomlion Gh Ltd/EHSU |
|  |  | Complete the acquisition of 1No. final solid waste disposal site | Anfoega | X | X | X | X |  | 3000.00 |  |  |  |  | xxx | Cent Admin | Wks/EHSU |
|  |  | Siting for at least 10 home burials, pauper burials (chemical agents, blanket, etc.) | Anfoega | X | X | X | X |  | 5000.00 |  |  |  | xxx |  | Cent Admin | EHSU |
|  |  | Prosecution of at least 20 sanitary offenders | Vakpo | X | X | X | X |  |  |  | 1000.00 |  | xxx |  | Cent Admin | EHSU |
|  |  | Convey 12No. staff meeting | Anfoega | X | X | X | X |  | 1,500.00 |  |  |  | xxx |  | EHSU | Cent Admin |
|  |  | Conduct 1No. refresher training for 17 staff /monitoring team | Anfoega | X | X | X | X |  | 2,500.00 |  |  |  | xxx |  | EHSU | Cent Admin |
|  |  | Update of DESSAP/Data collection | Anfoega | X | X | X | X |  | 15,000.00 |  |  |  | xxx |  | EHSU | DPCU |
|  |  | Repair of 1No. Office printer and computer. | Anfoega | X | X | X | X |  | 1000.00 |  |  |  | xxx |  | Cent Admi. | EHSU |
|  |  | Purchase of 2No. cabinet for office use | Anfoega | X | X | X | X |  | 6,500.00 |  |  |  | xxx |  | Cent Admi. | EHSU |
|  |  | Purchase of 1No.Motorbike | Anfoega | X | X | X | X |  | 5000.00 |  |  |  | xxx |  | Cent Admi. | EHSU |
|  |  | Repair 10No. broken down boreholes across the District | District wide | X | X | X | X |  | 100,000.00 |  |  |  | xxx |  | Cent Admin | Wks Dept/MWST |
|  |  | Construct and mechanize 15No. boreholes | District wide | X | X | X | X |  | 200,000.00 |  |  |  | xxx |  | Cent Admin | Wks Dept/MWST |
|  |  | Rehabilitate Water Closet toilet in Anfoega market | Anfoega | X | X | X | X |  |  |  | 50,000.00 |  |  |  | Cent Admin | Wks Dept |
| Goal: To enhance access to quality healthcare Objectives: To improve CHPS coverage and functionality from 80% to 100% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Health delivery | Complete construction of 1No. CHPS Compounds at Wadamaxe, | Wadamaxe | X | X | X | X |  | 200,000.00 |  |  |  |  | xxx | Cent Admin | Health Dep’t/Wks Dept |
|  |  | Complete construction of 1No. CHPS Compounds at Tsrukpe -Tota | Tsrukpe Tota | X | X | X | X |  | 200,000.00 |  |  |  |  | xxx | Cent Admin | Health ’t/Wks Dept |
|  |  | Construct 1No. CHPS Compounds at Ando | Ando | X | X | X | X |  | 200,000.00 |  |  |  |  | xxx | Cent Admin | Health Dep’t/Wks Dept |
|  |  | Construct 1No. maternity wards at Wusuta Kpebe CHPs | Wusuta Kpebe | X | X | X | X |  |  | 250,000.00 |  |  | xxx |  | Cent Admin | Health Dept/Wks Dept |
|  |  | Construct 1No. maternity wards at Botoku CHPs | Botoku | X | X | X | X |  |  | 250,000.00 |  |  | xxx |  | Cent Admin | Health Dept/Wks Dept |
|  |  | Construct 1No. maternity ward at Awate-Todzi | Awate | X | X | X | X |  |  | 250,000.00 |  |  | xxx |  | Cent. Admi. | Health Dept./Wks |
|  |  | Support NID/Malaria Control Programmes | Vakpo | X | X | X | X |  | 10,000.00 |  |  |  |  | xxx | Health Dept | Cent.Admi |
|  |  | Review meetings for all key stakeholders. | Anfoega | X | X | X | X | 5000.00 |  |  |  |  |  | xxx | Health Dept | Cent.Admi |
|  |  | Quarterly monitoring of health facilities | District wide | X | X | X | X | 2,500.00 |  |  |  |  |  | xxx | Health Dept | Cent.Admi |
| Goal: To eliminate the incidence of malnutrition Objectives: To reduce the incidence of starvation especially among children under 12yrs by 50% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Health delivery | Procure Eight 8No. cartons of plumpy nuts and fbt annually | Anfoega | X | X | X | X |  | 20,000.00 |  |  |  | xxx |  | Health Dep’t | Cent Adm |
|  |  | Procure special measurement bowls and scales for preparation of feed for in-patients | Anfoega | X | X | X | X |  | 5,000.00 |  |  |  |  |  | Health Dep’t | Cent Adm |
|  |  | Organise training programme for nurses on infant and young child feeding. | Anfoega | X | X | X | X |  |  |  | 5,000.00 |  | xxx |  | Health Dept. | Cent Adm |
|  |  | Procure 31No. Electronic weighing scales, 31No plastic tables, 155No. Chairs and 5No. Motor cycles. | District wide | X | X | X | X |  |  | 50,000.00 |  |  | xxx |  | Health Dep’t | Cent Adm |
| Goal: To eliminate the incidence of HIV/AIDS and other STI’s Objectives: To reduce the prevalence rate of the virus from 1.2% to 0.5% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Health delivery | Quarterly DAC meetings | Anfoega | X | X | X | X |  | 6,000.00 |  |  |  | xxx |  | HIV/AIDs Desk | CentAdm |
|  |  | Monitoring of CBOs, NGOs, PMTCT & ART centers | District wide | X | X | X | X |  | 2,500.00 |  |  |  | xxx |  | HIV/AIDs Desk | CentAdm |
|  |  | Support 3 Persons Living with HIV (PLHIV) under emergency. | District wide | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | HIV/AIDs Desk | Cent.Admi. |
|  |  | Counseling and testing on HIV/AIDs during National Celebrations. | Venue for celebration. | X | X | X | X |  | 1,500.00 |  |  |  | xxx |  | HIV/AIDs Desk | Cent. Admi. |
|  |  | Advocacy on PMTCT, | Anfoega | X | X | X | X |  | 1,500.00 |  |  |  | xxx |  | HIV/AIDs Desk | Cent. Admi. |
|  |  | Stigma reduction and resource mobilization. | District wide | X | X | X | X |  | 1000.00 |  |  |  | xxx |  | HIV/AIDs Desk | Cent. Admi. |
|  |  | Celebrate World AIDS Day annually | Selected community | X | X | X | X |  | 1000.00 |  |  |  | xxx |  | HIV/AIDs Desk | Cent. Admi. |
| Goal: To expand and improve access to quality education infrastructure at all levels To improve the quality of teaching and learning at all levels Objective: To improve access to quality basic education infrastructure by 20% by the end of the planned period To improve BECE performance from 38% to 65% by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Education and youth development | Complete the Construction of 1No. 3-unit classroom blocks with ancillary facilities | Aveme Danyigba | X | X | X | X |  |  | 221,530.99 |  |  |  | xxx | Cent Admin | Wks |
|  |  | Complete the construction 1No. 2-unit K.G blocks with ancillary facilities | Vakpo Afeyi | X | X | X | X |  |  | 251,645.06 |  |  |  | xxx | Cent Admin | Wks |
|  |  | Complete the rehabilitation of 1No. 6Unit Classroom Block at VASEC | VASEC | X | X | X | X |  |  | 65,000.00 |  |  |  | xxx | Cent Admin | Wks |
|  |  | Complete the Rehabilitation of Aveme Beme JHS | Aveme Beme | X | X | X | X |  |  | 50,000.00 |  |  |  | xxx | Cent Admin | Wks |
|  |  | Complete the Construction of 1No. 4-Unit Classroom Block at wusuta Anyafo | Wusuta Anyafo | X | X | X | X |  |  | 234,769.80 |  |  |  | xxx | Cent Admin | Wks |
|  |  | Teacher carrier Development capacity workshops | Within the District | X | X | X | X |  | 30,000 |  | 20,000 |  | xxx |  | Edu. Dept | Cent Adm. |
|  |  | Construct 1No. 6Unit Classroom Block at VASEC | Vakpo | X | X | X | X |  |  | 650,000.00 |  |  | xxx |  | Cent Adm | Educ Dep’t/Wks |
|  |  | Complete the Construction of 1No. 2Unit Teachers Bungalow at ASTECH | VASTECH | X | X | X | X | 280,000.00 |  |  |  |  |  | xxx | Cent Adm | Wks |
|  |  | Construct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Complete Construction of 1No. 2Unit Teachers Bungalow | ANFOESEC | X | X | X | X | 280,000.00 |  |  |  |  |  | xxx | Cent Adm | Wks |
|  |  | Organise My First Day at School Programme for KG & Prim. 1 | District wide | X | X | X | X |  | 30,000.00 |  |  |  | xxx |  | Cent Adm | EducDep’t |
|  |  | Complete construction of 1No. 6Unit Classroom block at Vakpo Konda | Vakpo Konda | X | X | X | X | 600,000.00 |  |  |  |  |  | xxx | CODA | Cent Adm |
|  |  | Support Brilliant but Needy Students (DA) | District wide | X | X | X | X |  | 25,000.00 |  |  |  | Xxx |  | Cent Adm | EducDep’t |
|  |  | Organize International Literacy Day celebration. | District wide | X | X | X | X |  | 2000.00 |  |  |  | Xxx |  | Cent Adm | NCCE |
|  |  | Organize 4No. stakeholder’s engagement to enhance education delivery in the District | Anfoega | X | X | X | X |  | 15,000.00 |  |  |  | xxx |  | Cent Adm | DEOC |
|  |  | Procure school furniture (Mono & Dual Desk) for schools in the District | Anfoega | X | X | X | X |  |  | 200,000.00 |  |  | xxx |  | Cent Adm | Proc |
| Goal: To enhance access to quality education by all at all levels Objective: To reduce drop-out rate by 20% especially among girls at basic school level annually |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Service Delivery | Education and youth development | Support teachers and children award | District wide | X | X | X | X |  | 20,000.00 |  |  |  | Xxx |  | Cent Adm | EducDep’t |
|  |  | Facilitate access to scholarship for 80 brilliant but needy students at the tertiary level | District wide | X | X | X | X |  |  |  | 2000.00 |  | xxx |  | Cent Adm | EducDep’t |
| Goal: To promote and develop available local tourism potential sites to meet internationally acceptable standards Objective: To ensure an increase in the number of tourists visits by 5% annually by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic development | Trade, industry and tourism services | Explore, collate and document all potential tourist sites in the District | District wide | X | X | X | X |  | 2,000.00 |  |  |  | xxx |  | Cent. Admi | DPCU |
|  |  | Design 2No. big size bill boards and 10No. Sign board at the potential tourist sites. | Anfoega | X | X | X | X |  | 4,500.00 |  |  |  | xxx |  | Cent Admin |  |
| Goal: To promote the development of modern market and transport infrastructure at all levels Objective: To ensure the construction of market sheds and stalls in 3 markets by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic development | Trade, industry and tourism services | Complete Pavement of Anfoega Market | Anfoega | X | X | X | X | 150,000.00 |  |  |  |  |  | xxx | CODA | Cent Adm |
|  |  | Construct 2No. warehouses at Vakpo Market | Vakpo | X | X | X | X |  |  | 60,000.00 |  |  | xxx |  | Cent Admin | Wks |
|  |  | Construct 2No. market stalls at Wusuta Kpebe Market | Wusuta Kpebe | X | X | X | X |  | 150,000.00 |  | 35,000.00 |  |  |  | Cent Admin | Wks |
|  |  | Construct Market Stores at Vakpo Market using partnership approach (PPP) | Vakpo | X | X | X | X |  |  |  |  | 400,000.00 | xxx |  | Cent Adm | Private sector/Wks |
|  |  | Construct 1No. Storey 30 Unit store (containers) at the Anfoega Lorry park. | Anfoega | X | X | X | X |  |  | 200,000.00 |  |  | xxx |  | Cent Adm | Wks |
|  |  | Construct passenger shed at the Anfoega Market Lorry Park | Anfoega | X | X | X | X |  |  | 120,000.00 |  |  | xxx |  | Cent Adm | Wks |
| Goal: To modernize agricultural production To improve post-harvest management To improves access to quality extension services by all farmers at all levels Objective: To improve irrigation farming by 5% by the end of the planned period To reduce post-harvest losses from 40% to 10% by the end of the planned period To reduce extension agent-farmer ratio from 1:709 to 1:500 by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural development | Organise 1No. Farmers’ Day celebration | Anfoega | X | X | X | X |  | 60,000.00 |  |  |  |  |  | Cent Admin | Agric Dep’t |
|  |  | Raise and distribute 200,000 cashew seedlings under GPSNP at Awate | Awate | X | X | X | X | 100,000.00 |  |  |  |  |  | xxx | GPSNP | Cent Adm/Agric Dep’t |
|  |  | Maintain 25-acre cashew plantation at Wusuta Kpebe | Wusuta Kpebe | X | X | X | X | 224,000.00 |  |  |  |  |  | xxx | Cent Adm | GPSNP/Comm |
|  |  | Raise and distribute 50,000 Cocoa seedlings at Vakpo Afeyi | Vakpo Afeyi | X | X | X | X | 100,000.00 |  |  |  |  |  | xxx | Agric Dep’t |  |
|  |  | Maintain 25-acre cashew plantation at Awate | Awate | X | X | X | X | 224,000.00 |  |  |  |  |  | xxx | Cent Adm | GPSNP/Comm |
|  |  | Pay for utilities | Vakpo | X | X | X | X | 16,000.00 | 1000.00 |  |  | 2000.00 | xxx |  | Agric Dep’t | Cent Adm |
|  |  | procure insurance policy and roadworthy certificate for official vehicle and motorbikes | Vakpo | X | X | X | X |  |  |  |  | 6,450.00 |  |  | Agric Dep’t | Cent Adm |
|  |  | Maintain 1No. Official vehicle and 9No. motorbikes | Vakpo | X | X | X | X |  |  |  |  | 7,600.00 |  |  | Agric Dep’t | Cent Adm |
|  |  | Office supply, stationery and maintain office equipment | Vakpo | X | X | X | X | 5000.00 |  |  |  |  | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Procure 5No. tyres (245/70 R16) for official vehicle | Vakpo | X | X | X | X | 20,000.00 |  |  |  | 12,000.00 | xxx |  | Agric Dep’t | Cent admi |
|  |  | Participate in sector workshops, meetings and Conferences by staff. | Vakpo | X | X | X | X | 4000.00 |  |  |  | 3,200.00 | Xxx |  | Agric Dep’t | Cent adm |
|  |  | Organize Monthly Technical Review Meetings for staff | Anfoega | X | X | X | X |  |  |  |  | 4000.00 | Xxx |  | Agric Dep’t | Cent adm |
|  |  | Participate in TEDMAG training. | Ho. | X | X | X | X | 25,000.00 |  |  |  |  | Xxx |  | Agric Dep’t | Cent adm |
|  |  | Organize district-wide and zonal RELC meetings | District wide | X | X | X | X | 25,000.00 |  |  |  |  | Xxx |  | Agric Dep’t | Cent adm |
|  |  | Supervise and monitor activities of AEAs and DAOs by DDA, DCD and others. | District wide | X | X | X | X |  | 5,000.00 |  |  | 5,000.00 | Xxx |  | Agric Dep’t | Cent Adm |
|  |  | Supervise the activities of AEAs by DAOs | District wide | X | X | X | X |  |  |  |  | 4,800.00 | Xxx |  | Agric Dep’t | Cent Adm |
|  |  | Train staff in Report writing skills | Anfoega | X | X | X | X |  |  |  |  | 4,500.00 | Xxx |  | Agric Dep’t | Cent Adm |
|  |  | Conduct yield studies in 4 main value chain crops (maize, rice, cassava and garden egg) | District wide | X | X | X | X | 20,000.00 |  |  | 3000.00 |  | Xxx |  | Agric Dep’t | Cent Adm |
|  |  | Procure vaccines and vaccinate dogs, Small Ruminants and Poultry. | District wide | X | X | X | X |  |  |  |  | 9,600.00 | Xxx |  | Agric Dep’t | Cent Adm |
|  |  | Conduct disease surveillance in both crops and Livestock | District wide | X | X | X | X |  |  |  |  | 5,000.00 | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Create awareness on agricultural programmes through community engagement/fora | District wide | X | X | X | X |  |  |  | 3,500.00 |  | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Train cassava processors (women groups) on value addition by producing quality gari | District wide | X | X | X | X |  |  |  | 1,500.00 | 3,500.00 | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Establish 8No demonstrations in Maize, Vegetables and Home garden in 4 Zones | Four Zones | X | X | X | X |  |  |  |  | 7,400.00 | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Train participants of Rearing for Food and Jobs (RFJ) programme on feed formulation and Monitor progress | District wide | X | X | X | X |  |  |  | 2000.00 | 2000.00 |  | xxx | Agric Dep’t | Cent Adm |
|  |  | Procure and distribute agricultural input to farmers | District wide | X | X | X | X |  | 20,000.00 |  |  |  | xxx |  | Cent Adm | Agric. Dept |
|  |  | Operate and maintain pack house at Vakpo | Vakpo | X | X | X | X |  |  |  | 10,000.00 |  | xxx |  | Agric Dept | Cent Adm |
|  |  | Support tree planting programme in the District (Greening Ghana programme) | District wide | X | X | X | X |  | 5,000.00 |  |  | 6,400.00 | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Embark on field and home visits by technical Staff | District wide | X | X | X | X |  | 24,000.00 |  |  |  | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Introduce and train participants in bee keeping in one community as an alternative livelihood activity | Selected communities | X | X | X | X |  |  |  |  | 6000.00 |  |  | Agric Dep’t | Cent Adm |
|  |  | Organize public education on prevention and management of HIV/AIDS, COVID 19 in the district | District wide | X | X | X | X |  | 1000.00 |  |  | 1000.00 | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Organize public education on Child labour and occupational hazard prevention. | District wide | X | X | X | X |  | 1,000.00 |  |  |  | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Educate FBOs on Climate Smart agricultural interventions. | District wide | X | X | X | X |  |  |  |  | 4,000.00 |  |  | Agric Dep’t | Cent Adm |
|  |  | Complete Rehabilitation of small Earth Dam at Vakpo Konda | Vakpo Konda | X | X | X | X | 224.000.00 |  |  |  |  |  | xxx | GPSNP | Cent Adm |
|  |  | Monitor progress of the operations of the Planting for Export and Rural Development (PERD) | District wide | X | X | X | X | 2,000.00 |  |  |  |  | xxx |  | Agric Dep’t | Cent Adm |
|  |  | Train staff and 40 attendants on tree crop nursery activities | Vakpo | X | X | X | X |  |  |  | 1000.00 | 11,000.00 | xxx |  | Agric Dep’t | Cent Adm |
| Goal: To enhance access to credit facilities by SME’s To reduce unemployment to its barest minimum Objective: To facilitate access to soft credit facilities by 100 registered SME’s annually To facilitate the registration of 100 SME’s annually with the Registrar General’s Department and the Assembly To reduce unemployment among the economically active age group by 40% annually by the end of the planned period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic development | Trade, industry and tourism services | Training 30 MSMEs in value addition and packaging | Anfoega | X | X | X | X | 3,500.00 |  |  |  |  | xxx |  | BAC | Cent Adm |
|  |  | Engagement with financial institutions for education on their services and credit conditions | Anfoega | X | X | X | X |  | 3,500.00 |  |  |  | xxx |  | BAC | Cent Adm |
|  |  | Income generation activities training | Anfoega | X | X | X | X |  | 10,000.00 |  |  |  | xxx |  | BAC | Cent Adm |
|  |  | Training in customer care and marketing skills | Anfoega | X | X | X | X |  | 6,000.00 |  |  |  | xxx |  | BAC | Cent Adm |
|  |  | A2E provision of startup kits | District wide | X | X | X | X |  |  | 20,000.00 |  |  |  |  | BAC | Cent Adm |
|  |  | Facilitating RGD registration | Anfoega | X | X | X | X |  |  |  | 500.00 |  |  |  | BAC | Cent Adm |
|  |  | Stakeholder’s forum | Anfoega | X | X | X | X |  |  |  | 500.00 |  |  |  | BAC | Cent Adm |
|  |  | MSMEs committee meeting | Anfoega | X | X | X | X |  | 2,180.00 |  |  |  | xxx |  | BAC | Cent Adm |